## Sheet1
1. Define the core features and functionalities that CityScope should have based on initial research and user stories. | 2023-09-15 | 2023-10-08
2. Design a wireframe mockup for the different pages of the web application. | 2023-10-08 | 2023-11-08
3. Set up the project architecture, deciding on tech stack and database choice. | 2023-09-15 | 2023-10-15
4. Establish data schemas for storing place information, including ratings, features, and location details. | 2023-10-05 | 2023-10-25
5. Curate a comprehensive database of places in Cincinnati, ensuring it has attributes relevant to user preferences. | 2023-10-05 | 2023-10-10
6. Design the recommendation algorithm for filtering places based on user inputs, with the ability to handle various criteria. | 2023-11-01 | 2023-01-01
7. Implement the front-end interface, allowing users to easily input their preferences and receive tailored recommendations. | 2023-11-01 | 2023-01-01
8. Code the backend logic that interacts with the database to fetch and display place recommendations. | 2023-10-01 | 2023-01-01
9. Create a visually appealing results page to display the recommended places with essential details and images. | 2023-02-01 | 2023-04-01
10. Conduct unit tests to ensure individual components function as expected. | 2023-04-01 | 2023-05-01
11. Add a feature to calculate and suggest optimal visiting times for each place, using historical data or crowd prediction algorithms. | 2023-11-01 | 2023-12-01
12. Integrate an interactive map that plots recommended places and allows users to view them based on proximity. | 2023-12-01 | 2023-01-01
13. Implement the daily itinerary generator, curating a list of places to visit within a day based on user selections. | 2023-11-01 | 2023-12-01
14. Validate the user experience by doing usability testing, ensuring the application is intuitive and meets user needs. | 2023-03-01 | 2023-04-01
15. Conduct integration tests to ensure all components work seamlessly together. | 2023-03-01 | 2023-04-01
16. Look for third-party APIs or partnerships that can enhance the application, such as integrating user reviews or booking capabilities. | 2023-11-01 | 2023-12-01
17. Conduct stress tests to ensure the platform can handle a high number of concurrent users. | 2023-03-01 | 2023-04-01
18. Iterate on the recommendation algorithm, ensuring it continually improves and adapts to user feedback. | 2023-10-01 | 2023-12-01
19. Write user manuals or guides to help users get the most out of CityScope. | 2023-03-01 | 2023-04-01
20. Integrate user feedback mechanisms directly into the app for continuous improvement and direct user engagement. | 2023-04-01 | 2023-05-01
21. Research how to use android studio for app development | 2023-09-01 | 2023-10-15
22. Design the app's UI | 2023-10-01 | 2023-12-01
23. Perform UI Testing | 2023-03-01 | 2023-04-01
24. Integrate 'Google Maps Platform API' into the app to retreive data related to location, reviews, ratings, etc | 2023-11-01 | 2023-12-01
25. Research how to utilize Java in the context of an android application | 2023-09-01 | 2023-11-01